## Sheet1
Task | Start Date | End Date
Data Collection and Cleaning | 2024-12-19 | 2024-12-22
Dataset Integration | 2024-12-22 | 2024-12-24
Exploratory Data Analysis (EDA) | 2024-12-24 | 2024-12-27
Data Visualization with Matplotlib | 2024-12-27 | 2024-12-30
Interactive Visualizations with D3.js | 2024-12-30 | 2025-01-01
Statistical Analysis | 2025-01-01 | 2025-01-04
Dashboard Creation | 2025-01-04 | 2025-01-06
Final Report and Presentation | 2025-01-06 | 2025-01-09